## Tabelle1
| Art | Other
| Programming | Testing
2 0 1 8
January |  |  | February |  |  | March | April | May | June |  | July |  | August
Create Skins -- Tsotne |  |  | Create Skins -- Tsotne |  | Make UI Icons -- Tsotne |  |  |  | Testing -- All | Stable | Create a Website -- Tsotne, Jan, (Sandro?) | Alpha Tests -- Closed?
2 New Healing classes -- All | [9 empty] | Alpha
|  | Finish UI -- Jan, Kyle |  |  |  | Get local Multiplayer ready for 4 players -- Jan |  |  |  | 2018-06-30
Implement Basic Network functionality -- Kyle
Animator Redesign/MECHANIM -- Sandro
Gamemodes -- Sandro